1140-A

SOCIAL MEDIA
IMPLEMENTATION PLAN

BRENDAN SAGALOW + MIKE CANNON

Cape Cod  •  Saturday, August 29, 2026

Campaign window Start: Monday, 20 July 2026 Finish: Event day, Saturday, 29 August 2026 Public placeholders: venue, town, ticket price, ticket link, age guidance, merchandise and any clam-bake details are TO BE DETERMINED. Working public line: CAPE COD • AUGUST 29 • GET YOUR TICKETS NOW AT [TBD SHORT URL]

| Built for a limited-time operator • A complete Core Run that can be maintained with one weekly batch session and brief check-ins. • High-return upgrades are separated from optional extras. • No daily improvisation is required until the final week. | The central rule • Use the comedians' existing content and accounts wherever permission allows. • One clean master clip can feed Instagram, Facebook, TikTok, YouTube Shorts and Stories. • Every post carries the date and a direct route to tickets. |
| --- | --- |

Prepared as an implementation document. Platform mechanics checked 18 July 2026.

# 1. Start here: the campaign in one page

Core Run: complete this first Create and secure the six main accounts; publish from one consistent 1140-A identity. Obtain approved clean clips, images, captions and repost/advertising permission from Forza. Publish three short videos each week on Instagram/Facebook and TikTok; publish one or two YouTube Shorts each week. Run a public Facebook Event and share it into relevant local groups at launch and in the final week. Use one coordinated Instagram Collab launch post and native reposts of artist/podcast content. Reply to comments and direct messages for ten minutes on four or five days each week. Post daily Stories from 17 August and one short video per day from 24–29 August. Keep one ticket link, one short URL and source tracking on every platform.

High-return upgrades One Cape-specific joint video from Brendan and Mike. Artist-originated Instagram Collab posts, Meta Partnership Ads and one TikTok Spark Ad. A supporter share pack for board members, friends, radio partners and charity contacts. One live or pre-recorded joint question-and-answer clip. Weekly local Facebook-group placement and radio-giveaway reposts.

Extra reach Threads and X scheduling, Reddit where community rules allow, Nextdoor, LinkedIn and Bluesky. Instagram Trial Reels, TikTok Duet/Stitch and a brief behind-the-scenes series. Sponsor, merchandise or clam-bake content only after every fact and permission is final.

Time budget

| Operating level | Typical weekly time | What it covers |
| --- | --- | --- |
| Core Run | About 2–3 hours | One 60–90 minute batch; 10-minute engagement checks on four or five days; one 15-minute review. |
| High-return upgrades | + about 60–90 minutes | Collabs, artist coordination, local groups, radio partner posts and paid-ad creative. |
| Extra reach | + about 1–2 hours | Secondary platforms, extra edits and optional community posting. |
| Final week | About 20 minutes daily | One short post, Stories, replies, ticket-link checks and event-day preparation. |

Stop line When time is short, complete the Core Run and stop. Do not replace it with scattered activity across every platform.

# 2. Event facts and placeholders

| Field | Approved public value |
| --- | --- |
| Presenter | 1140-A, a Cape-based non-profit |
| Performers | Brendan Sagalow and Mike Cannon |
| Date | Saturday, August 29, 2026 |
| Area | Cape Cod, Massachusetts |
| Venue and town | TO BE DETERMINED |
| Doors and show time | TO BE DETERMINED |
| Ticket price and tiers | TO BE DETERMINED |
| Ticket link | TO BE DETERMINED |
| Short ticket URL | TO BE DETERMINED — recommended form: 1140-A.org/aug29 |
| Age/content guidance | TO BE DETERMINED — use only wording approved by Forza and the venue |
| Merchandise | TO BE DETERMINED |
| Sponsor | TO BE DETERMINED |
| Clam-bake or VIP add-on | TO BE DETERMINED; do not mention until capacity, price, eligibility and delivery are final |
| Official social handle | TO BE DETERMINED; preferred: @1140AComedy |
| Media/social contact | TO BE DETERMINED |

Approved working language

[ ] Primary consumer line: Brendan Sagalow + Mike Cannon — together on Cape Cod, August 29.

[ ] Mission line: A Cape-based non-profit bringing nationally touring stand-up comedy to Cape audiences.

[ ] Joint-content line: Long-time collaborators and current Fart Carnival co-hosts, together on one Cape Cod stage.

[ ] Do not call the event clean, family-friendly, a live podcast, a Cape debut or sold out unless Forza and the facts support the claim.

Public graphic line BRENDAN SAGALOW + MIKE CANNON CAPE COD • AUGUST 29 GET YOUR TICKETS NOW AT [TBD SHORT URL] Presented by 1140-A, a Cape-based non-profit

# 3. Open, secure and connect the accounts

Account identity

| Item | Use this |
| --- | --- |
| Preferred handle | @1140AComedy |
| Fallback handles | @1140ACompany; @1140ACapeCod |
| Display name | 1140-A ¦ Cape Cod Comedy |
| Profile photograph | 1140-A logo on a plain, high-contrast background |
| Bio | Cape-based non-profit presenting live stand-up. Brendan Sagalow + Mike Cannon • August 29 • Cape Cod. Tickets: [TBD] |
| Primary link | One direct ticket link or branded redirect; avoid a multi-link page during this single-event campaign |
| Location | Cape Cod, Massachusetts |
| Contact button | Organisation email controlled by 1140-A |

Accounts to create — in this order

| Order | Account | Use |
| --- | --- | --- |
| 1 | Instagram professional/business account | Main short-video and Collab account |
| 2 | Facebook Page + one public Facebook Event | Local discovery, groups, event updates and Meta ads |
| 3 | TikTok public business account | Native clips, reposts and possible Spark Ads |
| 4 | YouTube Brand channel | Shorts, search presence and a permanent clip library |
| 5 | Threads linked to Instagram | Lightweight local/conversational reposting |
| 6 | X account | Lightweight press, radio and comedy-network reposting |
| Optional | LinkedIn, Nextdoor, Reddit and Bluesky | Only after the Core Run is scheduled |

Security and access checklist

[ ] Use an organisation-controlled email address, not the volunteer's personal email.

[ ] Store passwords in a password manager; use a unique password for each platform.

[ ] Turn on two-factor authentication and store recovery codes with the 1140-A owner.

[ ] Give the social lead delegated/shared access where the platform offers it; do not circulate one password to several people.

[ ] The 1140-A owner remains full administrator. The social lead receives publishing, comment and insight access.

[ ] Add one back-up administrator who is not the social lead.

[ ] Write the official ticket link, approved facts and emergency contact in the shared folder.

[ ] Set a calendar reminder to remove temporary access after the event and archive recovery codes.

Pin these posts

| Platform | Pinned content |
| --- | --- |
| Instagram | Launch Collab Reel; strongest comedian clip; final event-information post |
| Facebook | Main Event/ticket post |
| TikTok | Launch clip; strongest Mike or joint clip; final-week ticket clip |
| Threads / X | One current ticket post |
| YouTube | Feature the event Short or playlist on the channel home page where available |

# 4. Roles, approvals and the content hand-off

| Owner | Decides / supplies |
| --- | --- |
| 1140-A owner | Final event facts, ticket link, money, legal claims, sponsor/charity decisions and crisis replies |
| Social lead | Scheduling, captioning, native posting, reposting, daily replies, tracking and weekly report |
| Forza / artists | Approved billing, clips, photographs, credits, collaboration acceptance, organic support and paid-ad permissions |
| Venue | Approved location wording, access/parking facts, event co-hosting and event-day filming rules |
| Ticketing provider | Purchase tracking, UTM preservation, checkout reporting and customer-service contact |

Request this package from Forza

[ ] One 30–45 second joint vertical video: both names, Cape Cod, August 29 and the ticket call-to-action.

[ ] One 15–20 second vertical video from Brendan and one from Mike.

[ ] Eight to twelve clean 9:16 clips with no platform watermark, baked-in logo or unlicensed music.

[ ] Two horizontal clips for Facebook/YouTube/news use.

[ ] Approved individual and joint photographs, with photographer credits.

[ ] Written organic-use and paid-ad-use permission for each supplied file.

[ ] A launch-day Instagram Collab commitment and one final-week share from each comic.

[ ] Meta Partnership Ad permission or code for the best artist post.

[ ] A TikTok Spark authorisation code for the best Mike, Brendan or joint post; request a 60-day window.

[ ] Approved podcast wording and permission to repost Fart Carnival clips.

[ ] One person at Forza who can approve routine posts within one business day.

Approval rule Keep a shared folder with four subfolders: 01 APPROVED; 02 SCHEDULED; 03 POSTED; 04 DO NOT USE. Only files in APPROVED may be edited or posted. Every approved asset record should include: platforms allowed, organic/paid status, expiry date, required credit and source link.

File naming

Use this pattern YYYYMMDD_ARTIST_TOPIC_LENGTH_FORMAT_RIGHTS Example: 20260811_JOINT_CAPEANNOUNCE_35S_9x16_ORGANIC-PAID.mp4

# 5. Platform priority and posting rhythm

Priority is based on the uploaded social-statistics workbook, pulled 18 July 2026. Figures are public-facing snapshots and some platform counts are approximate.

| Rank | Channel | Level | Action |
| --- | --- | --- | --- |
| 1 | Instagram + Facebook | Highest | Brendan: about 146.7K on Instagram. Mike: about 83.4K. Combined Facebook pages: about 118K. Run one Meta workflow, one Facebook Event and local-group sharing. |
| 2 | TikTok | Highest | Mike: about 174K followers and 4.2M likes. Brendan: about 44.8K and 1.9M likes. Use Mike-led and joint clips; request Spark authorisation. |
| 3 | YouTube Shorts | Core secondary | Both artist channels have about 16K subscribers; proven Shorts range from about 75K to 285K views. Upload approved clips natively. |
| 4 | Facebook Groups | High local value | Use the Page/Event at launch and once in the final week; observe each group's rules. |
| 5 | Threads + X | Maintenance | Schedule two or three concise posts per week and quote/repost artists, radio and press. Do not spend paid budget here. |
| 6 | Nextdoor / Reddit / LinkedIn / Bluesky | Extra reach | Use only after the main content is scheduled. No paid budget at this scale. |

Core posting cadence

| Channel | Frequency | Execution |
| --- | --- | --- |
| Instagram Reels + Facebook Reels | 3 per week through 16 August; 4 during 17–23 August; 1 daily from 24–29 August | Use the same clean master; upload/cross-post through Meta without an external watermark. |
| Instagram/Facebook Stories | 3 days per week through 16 August; daily from 17 August; 3–6 frames per day in the final 72 hours | Clip + date + link sticker; radio/artist reposts; FAQ answers. |
| TikTok | 3 per week; 4 during 17–23 August; 1 daily from 24–29 August | Native upload, different caption; Mike and joint clips first. |
| YouTube Shorts | 1–2 per week; 2 during the final week | Short URL on screen; artist @mentions in title/description. |
| Facebook Event | 1 update per week; 3 updates in event week | New clip, practical information, final reminder. |
| Threads + X | 2–3 per week | Schedule concise copy and direct links; use for partner reposts. |
| Comments and DMs | 10 minutes on 4–5 days each week; daily from 17 August | Answer, thank, hide scams and move complex matters to email/DM. |

Starting posting windows — Eastern Time

| Use | Starting window |
| --- | --- |
| Weekday short video | 6.30–8.30 p.m. |
| Weekday practical or press/radio post | 11.30 a.m.–1.00 p.m. |
| Weekend short video | 9.00–11.00 a.m. or 5.00–7.00 p.m. |
| Launch Collab | Aim for 10.00 a.m. on 21 July; use Forza's chosen time if different |
| Final 72 hours | Morning information; evening comedian clip; Stories between |
| Adjustment | After two weeks, use each platform's Insights and move to the strongest actual times |

Volume cap Before 24 August: no more than one feed post per platform per day. Final week: one short video per day is sufficient. Use Stories for extra updates. Do not create filler merely to post often. Repost relevant artist, podcast, radio and press content instead.

# 6. Reposting, grouping and artist-account mechanics

A. Instagram Collab post — the launch priority [M1]

1. Choose the origin account. Best: an artist account originates and invites the other comic plus 1140-A. Fallback: 1140-A originates and invites both artists if the app offers the required collaborator slots.

2. Prepare the final 9:16 video, caption, location tag, ticket link in bio and exact launch time.

3. In Instagram: create the Reel → Tag people → Invite collaborator → select the approved accounts.

4. Tag the venue and media/radio partners normally; do not use collaborator status without agreement.

5. Send Forza a screenshot and ask the artists to accept the Collab request as soon as it is live.

6. Fifteen minutes later, share the Reel to Stories with a ticket-link sticker.

7. Pin the Reel on 1140-A. Keep it pinned until the final event-information post replaces it.

Launch caption CAPE COD: Brendan Sagalow and Mike Cannon are together for one night on Saturday, August 29. [VENUE/TOWN – TBD]. Tickets: [TBD SHORT URL]. @brendansagalow @iammikecannon @fartcarnival #1140AComedy #CapeCodComedy #CapeCodEvents #StandUpComedy

B. Instagram native Repost + Story share [M2]

[ ] Use the native Repost icon on relevant public artist or Fart Carnival Reels/posts.

[ ] Add a short note where the feature allows it: 'Both on Cape Cod • August 29 • tickets in bio.'

[ ] Also share the strongest repost to the 1140-A Story with a link sticker.

[ ] Do not repost every artist upload. Select one relevant item per artist or podcast each week.

[ ] Do not screen-record or download public posts to add an event overlay. Use a supplied/approved file for the overlay version.

C. Facebook Page and Event

[ ] Create one public Event from the 1140-A Page; add venue/co-hosts only with approval.

[ ] Publish each core Reel to the Page and one Event update per week.

[ ] Share the Event into relevant local groups once at launch and once during 24–28 August.

[ ] When a radio station or media outlet posts, share its original post rather than copying it.

[ ] Keep the ticket link in the Event button and every Event update.

D. TikTok Repost, authorised clip and Spark Ad [T1–T3]

[ ] For simple support: open a public artist post → Share → Repost. Native reposts retain the original source.

[ ] A native repost cannot carry the full event end-card. For a sales post, upload an approved clean clip and add the Cape Cod/date/ticket slate.

[ ] Optional Duet/Stitch: use only when reuse is enabled and Forza approves commercial event promotion.

[ ] For paid reach: ask the artist/Forza for a Spark code for the exact post. No passwords are required.

[ ] Request a 60-day code; record the code, expiry and permitted budget in the asset tracker.

[ ] Upload natively to TikTok; never use a Reel with an Instagram watermark.

E. YouTube Shorts [Y1–Y4]

[ ] Upload the approved clean vertical clip through YouTube Studio and schedule the publish time.

[ ] Mention @BrendanSagalow, @MikeCannonComedy and @FartCarnival only when relevant.

[ ] Put the short ticket URL on screen and in the channel profile. URLs in Shorts descriptions/comments are not clickable.

[ ] Use YouTube Remix only when the source is eligible and Forza has approved the promotional use; supplied files are the default.

F. Threads and X

[ ] Quote/repost the artist, podcast, radio or press post and add the direct ticket link.

[ ] Use one or two @mentions, not a wall of tags.

[ ] Schedule two or three posts per week; use the final week for daily practical reminders only if time allows.

[ ] Do not prioritise the inactive Fart Carnival X account.

# 7. Podcast reposts and the first clip bank

Podcast rhythm Use Fart Carnival as proof of the pair's chemistry, not as the only content source. One joint/podcast post every seven to ten days is enough. For each new episode: Story share on release day; one feed clip only when the excerpt is especially strong. Always connect the clip to the live date in the caption and closing slate.

| Type | Candidate source | Snapshot | Best use | Link |
| --- | --- | --- | --- | --- |
| Joint | Why do we put this stuff in our bodies? | 26,077 YouTube views | Launch-week or week-two joint chemistry | Open |
| Joint | Brendan has been a comedian since middle school | 11,833 | Meet-the-comics / history | Open |
| Joint | The Perfect Heist | 11,518 | Long-form source for a clean joint cut | Open |
| Joint | Brendan learns basketball — Coach Cannon | 5,612 | Playful pairing / TikTok | Open |
| Brendan | Freeze for Brittney | 284,527 | Strongest proved Brendan Short | Open |
| Brendan | He play too much | 24,944 | Short punchy clip | Open |
| Brendan | Thin Lips — full special | 101,495 | Source for an approved stand-up excerpt | Open |
| Mike | I got hit as a kid | 74,993 | Strongest recent Mike Short | Open |
| Mike | Am I artistic? | 23,270 | Second Mike test clip | Open |
| Mike | Live From Gramercy | 28,737 | Source for an approved stand-up excerpt | Open |

Rights warning The links above are a selection list for Forza. They are not automatic permission to download, edit, advertise or repost. Use native Repost/Story functions for public posts, or obtain the original clean file and written permission for edited and paid versions.

One approved clip becomes six outputs

| Master file | Outputs |
| --- | --- |
| Clean 9:16 video | Instagram Reel; Facebook Reel; TikTok; YouTube Short; Story cut; still frame for Threads/X |
| Joint 30–45 second announcement | Launch Collab; 15-second cut; 8-second final reminder; radio/social embed; paid Meta/TikTok versions |
| One photograph | 4:5 feed post; square radio graphic; Story; Event cover; press/social card |
| Five written answers | Carousel; caption bank; Q&A Stories; Threads/X posts; Facebook Event update |

# 8. Creative rules, captions and calls to action

Every short-video checklist

[ ] Vertical 9:16, ideally 1080 × 1920.

[ ] Open on a face, line or moment — no logo animation at the beginning.

[ ] Hook within the first one to two seconds.

[ ] Use burned-in captions and check every name and place spelling.

[ ] Keep the original joke audio clear; no music unless commercial use is cleared.

[ ] Place the event end-card for two to three seconds at the end.

[ ] Keep text away from the top, bottom and right-side interface areas.

[ ] Use one local location tag: Cape Cod, Massachusetts, or the confirmed venue location.

[ ] No watermark from another platform.

[ ] File name and rights recorded before scheduling.

End-card text

Standard end-card BRENDAN SAGALOW + MIKE CANNON CAPE COD • AUGUST 29 GET TICKETS: [TBD SHORT URL] 1140-A

Caption formula

| Line | Content |
| --- | --- |
| 1. Hook | The funniest or most specific sentence; no administrative opening. |
| 2. Event | Brendan Sagalow + Mike Cannon • Cape Cod • August 29. |
| 3. Context | One sentence explaining the clip, joint podcast or 1140-A local angle. |
| 4. Action | Tickets: [clickable link] or 'ticket link in bio'. |
| 5. Credit | Artist/podcast tags and source/photographer credit. |
| 6. Discovery | Three to five relevant hashtags on Instagram/TikTok; zero to two on Facebook/X. |

Content mix across ten feed posts

| Posts | Content |
| --- | --- |
| 5 | Strong comedian stand-up or podcast clips |
| 2 | Joint chemistry / Fart Carnival / shared history |
| 1 | Cape-based non-profit and local cultural mission |
| 1 | Practical event information and FAQ |
| 1 | Radio, press, audience proof or partner repost |

Graphics to build once

[ ] 9:16 video end-card.

[ ] 9:16 Story template with a clear link-sticker area.

[ ] 4:5 feed graphic for event facts.

[ ] Square radio/giveaway graphic.

[ ] Facebook Event cover.

[ ] Final-week 'THIS SATURDAY', 'TOMORROW' and 'TONIGHT' versions.

[ ] Sponsor/clam-bake/merch templates left blank until those details are confirmed.

# 9. Handles, hashtags and whom to follow

Artist and joint accounts — confirm in-app before launch

| Platform | Brendan | Mike | Joint |
| --- | --- | --- | --- |
| Instagram | @brendansagalow | @iammikecannon | @fartcarnival |
| TikTok | @brendansagalow | @iammikecannon | Use official joint account only if Forza confirms one |
| YouTube | @BrendanSagalow | @MikeCannonComedy | @FartCarnival |
| X | @BrendanSagalow | @IamMikeCannon | Do not prioritise inactive @fartcarnivalpod |
| Facebook | /Brendansagalow | /IamMikeCannon | Use official podcast Page if supplied |
| Threads | Confirm in-app | @iammikecannon | Confirm in-app |

Local accounts to follow and monitor

| Group | Accounts |
| --- | --- |
| News / events | @capecodtimes; @capecodcom; Cape & Islands public radio; Boston and South Shore outlets on the PR list |
| Tourism / community | @visitcapecod; @capecodchamber; @capecodlife; town chambers from the Upper and Mid-Cape |
| Venue | Venue and campus accounts — TO BE DETERMINED |
| Radio | @pixy103; @959watdfm; @959watdmornings; @coxswainmedia; search and verify Cape Country 104 and WBSM |
| Comedy network | @gasdigital; @beautifulboyspod; @nycomedyclub; @comedycellarusa; @donttellcomedy |
| Ticketing / partners | Ticketing provider; charity partners; sponsor and clam-bake provider only when confirmed |

Follow and engagement routine Day 1: follow the artists, podcast, venue/ticketing and five core local accounts. Days 2–7: add five to ten relevant local/comedy accounts per day; no follow/unfollow churn. Daily: like or reply only where the content is genuinely relevant to Cape events, comedy or the booked artists. Tag a large account only when the post directly features it or a partnership has been agreed.

Hashtag pool

| Use | Hashtags |
| --- | --- |
| Fixed brand | #1140AComedy |
| Cape | #CapeCod #CapeCodEvents #CapeCodComedy |
| Format | #StandUpComedy #LiveComedy #ComedyShow |
| Boston / Massachusetts | #BostonComedy #MassachusettsEvents |
| Artist | #BrendanSagalow #MikeCannon |
| Joint/podcast only | #FartCarnival |

Hashtag use by platform

| Platform | Use |
| --- | --- |
| Instagram | 3–5: one brand, one or two local, one format, one artist/joint tag |
| TikTok | 3–5; include clear search words in on-screen text and caption |
| Facebook | 0–2; prioritise readable copy and the direct link |
| Threads | One relevant topic tag where available |
| X | 0–2; use direct @mentions and link |
| YouTube | 0–3; put names, Cape Cod and date in the title/description |

# 10. Master campaign calendar: 20 July–29 August 2026

Core Run is the minimum. High-return and Extra reach tasks are used only after the Core Run is scheduled.

Week 1 — Set-up and coordinated launch  |  20–26 July

| Date | Core Run | High-return upgrade | Extra reach |
| --- | --- | --- | --- |
| Mon 20 Jul | Create/secure accounts; set bio, logo and one ticket-link placeholder. Create Facebook Page/Event draft. Build shared folders and tracker. | Send Forza the asset/permission request; agree launch time and Collab origin account. | Join relevant Facebook groups; create Threads/X/LinkedIn only after the six main accounts work. |
| Tue 21 Jul | Publish coordinated launch Collab Reel at agreed time; cross-post to Facebook; upload native TikTok; Story with link sticker; pin launch post. | Ask each artist and Forza to share/accept immediately. Send supporter share pack to the first trusted group. | Post a short Threads/X launch message with direct link. |
| Wed 22 Jul | Publish/finish Facebook Event; add event facts and ticket link. Reply to every comment/DM. Story: names + date + ticket link. | Invite approved venue/partner co-hosts; share Event in one or two high-quality local groups. | YouTube Community post if the new channel has access. |
| Thu 23 Jul | Post Brendan introduction clip to IG/FB Reels and TikTok; caption with Cape Cod/date/ticket CTA. | Upload the same clean master as a YouTube Short; ask Brendan account to repost/Story share. | Threads/X quote post using Brendan clip still. |
| Fri 24 Jul | Post Mike introduction clip to IG/FB Reels and TikTok; reply to comments. | Test a second opening hook on TikTok if a clean alternate cut exists. | Share to one Boston/South Shore events group if rules allow. |
| Sat 25 Jul | One 4:5 mission/date post: Cape-based non-profit + one-night live comedy. Story with ticket link. | Ask venue/charity/radio contacts to follow the account; do not request posts yet unless launch was agreed. | Optional Nextdoor/LinkedIn introduction. |
| Sun 26 Jul | 15-minute review: record views, shares, saves, profile visits, link clicks and ticket-source data. Schedule Week 2. | Choose the best launch creative for the first paid test. | No feed post; light replies only. |

Week 2 — Establish the pairing  |  27 July–2 August

| Date | Core Run | High-return upgrade | Extra reach |
| --- | --- | --- | --- |
| Mon 27 Jul | Batch and schedule the week's three short videos; update link/venue placeholders when confirmed. | Create two paid-ready cuts: one joint, one strongest individual. | Prepare a simple radio/giveaway square graphic. |
| Tue 28 Jul | Post a Fart Carnival/joint chemistry clip on IG/FB and TikTok. Story with ticket link. | Use Instagram Collab if Forza approves a second joint post. | YouTube Short from the clean joint clip. |
| Wed 29 Jul | Story-only day: podcast repost + 'both on Cape Cod August 29'. Reply to comments/DMs. | Use Instagram native Repost of the official podcast post and add a note. | Threads/X podcast quote with direct link. |
| Thu 30 Jul | Post strongest Brendan clip variation to IG/FB and TikTok. | Begin small Meta test only if ticket page and tracking are live. | Instagram Trial Reel if available and the main Reel has already been posted. |
| Fri 31 Jul | Facebook Event update; one local-group share with local opening line and event link. | Support any radio giveaway post by sharing the station's original to Stories. | LinkedIn non-profit post if sponsor/community audience matters. |
| Sat 1 Aug | Post strongest Mike clip to IG/FB and TikTok; use Mike tag and ticket CTA. | Ask Forza for TikTok Spark code if this or an artist-originated post performs best. | YouTube Short. |
| Sun 2 Aug | Review and schedule. Keep the top two creative formats; retire the weakest. | Record paid test results separately from organic results. | No feed post unless a major partner repost needs immediate support. |

Week 3 — Proof, personality and local relevance  |  3–9 August

| Date | Core Run | High-return upgrade | Extra reach |
| --- | --- | --- | --- |
| Mon 3 Aug | Batch three videos and one FAQ graphic. Confirm all TBD fields that are now final. | Prepare a documented social-proof carousel using only approved figures. | Build one Reddit/Nextdoor draft but do not post until rules are checked. |
| Tue 4 Aug | Post joint clip with on-screen 'CAPE COD • AUGUST 29'. | Use a new hook/crop rather than repeating Week 2 exactly. | Threads/X short quote from the clip. |
| Wed 5 Aug | Stories: poll or question box — 'Who are you bringing?' / 'Brendan or Mike clip next?'. Reply to answers. | Turn repeated audience questions into the FAQ graphic. | Share a relevant Cape events/tourism post if natural. |
| Thu 6 Aug | Post Brendan clip; add approved special/credential in one sentence. | Ask Brendan to share this post or use it as a Collab if available. | YouTube Short. |
| Fri 7 Aug | Post local mission/venue atmosphere graphic; Event update; ticket link. | Share in one or two different local groups; vary the first line and obey rules. | Tag a local account only if it is directly involved. |
| Sat 8 Aug | Post Mike clip; use parenting/family/personal material only where the clip itself supports it. | Test the clip as TikTok Spark or Meta Partnership Ad if authorised. | Threads/X with direct link. |
| Sun 9 Aug | Review: select one winning joint clip and one winning individual clip for the middle paid phase. | Check comments for content/age/parking questions; send unresolved facts to 1140-A owner. | No feed post. |

Week 4 — Conversion and coordinated artist support  |  10–16 August

| Date | Core Run | High-return upgrade | Extra reach |
| --- | --- | --- | --- |
| Mon 10 Aug | Batch content. Refresh pinned posts if the ticket/venue details are now final. | Confirm the Cape-specific artist video and final-week share dates with Forza. | Prepare supporter share pack #2. |
| Tue 11 Aug | Publish the Cape-specific joint video as the week's main Collab post. Cross-post and pin if stronger than launch. | Begin/scale the best authorised Meta Partnership Ad or TikTok Spark Ad. | Ask radio/media partners to repost the original rather than create a duplicate. |
| Wed 12 Aug | Stories: FAQ sequence — venue/town, time, ticket link, age guidance and accessibility, each only if confirmed. | Save FAQ Story to an Event highlight. | Threads/X FAQ link post. |
| Thu 13 Aug | Post a fresh Fart Carnival/podcast clip; close with ticket end-card. | Ask @fartcarnival to Collab/repost if approved. | YouTube Short. |
| Fri 14 Aug | Facebook Event update + second local-group round. Use 'two weeks away' only if exact. | Send supporter share pack #2 to trusted people and charity/radio contacts. | Optional Reddit/Nextdoor post where allowed. |
| Sat 15 Aug | Repost/re-cut the strongest individual clip with a new opening and direct CTA. | Place paid budget behind the organic winner, not a generic flyer. | One Threads/X social-proof post. |
| Sun 16 Aug | Review; schedule daily Stories from Monday. Check every platform bio and link. | Create final-week end-cards and captions now. | No feed post. |

Week 5 — Daily visibility and urgency  |  17–23 August

| Date | Core Run | High-return upgrade | Extra reach |
| --- | --- | --- | --- |
| Mon 17 Aug | Begin daily Stories. Batch four feed clips. Story: date, ticket link and best recent clip. | Create retargeting audiences if tracking allows: video viewers, social engagers and site visitors. | Prepare radio/press repost cards. |
| Tue 18 Aug | Post Brendan clip with an '11 days' or date-only end-card; TikTok and Meta. | Ask Brendan for final-week Story share date. | YouTube Short. |
| Wed 19 Aug | Story/podcast repost; feed quote card or joint clip only if it is strong. Reply to all comments. | Use question sticker for final FAQ collection. | Threads/X direct link. |
| Thu 20 Aug | Post Mike clip with direct ticket CTA; TikTok first, then IG/FB. | Run/refresh Mike Spark Ad if authorised and performing. | YouTube Short. |
| Fri 21 Aug | Practical post: 'Next Saturday' + confirmed venue/time/ticket facts. Event update. | Share in local groups whose rules allow a final reminder. | Partner reposts and radio giveaway support. |
| Sat 22 Aug | One-week joint video. Pin it if it contains all final event information. | Coordinated artist/Forza share; increase paid budget on the winner. | Supporter share pack #3. |
| Sun 23 Aug | Review final week. Check ticket link on every profile. Prepare Monday–Saturday posts and Stories. | Move the remaining paid budget to the two best creatives and retargeting. | No extra platform work until final-week assets are scheduled. |

Event week — One useful post per day  |  24–29 August

| Date | Core Run | High-return upgrade | Extra reach |
| --- | --- | --- | --- |
| Mon 24 Aug | Final-week joint clip: names, Cape Cod, Saturday, ticket link. Stories morning/evening. | Artist-originated Collab or partnership-ad version if available. | Threads/X; share any press/radio post. |
| Tue 25 Aug | Brendan-focused short. Story: ticket link + one confirmed practical fact. | Ask Brendan to share; use his strongest approved clip variation. | YouTube Short. |
| Wed 26 Aug | Mike-focused short. Story: ticket link + one confirmed practical fact. | Ask Mike to share; refresh Spark/partnership ad if this is the winner. | YouTube Short. |
| Thu 27 Aug | '48 HOURS' practical video/graphic. Confirm doors, location, parking, age and official ticket source. | Final local-group post and supporter share pack; share radio winner content. | Threads/X morning and evening reminders. |
| Fri 28 Aug | 'TOMORROW' artist or joint video. Stories: morning, afternoon, evening. Answer every genuine question. | Forza/artist final Story share; use remaining paid budget on retargeting and the top creative. | Behind-the-scenes venue preparation only with permission. |
| Sat 29 Aug | 8–9 a.m. TONIGHT post; noon practical Story; 3–4 p.m. final ticket Story; doors Story; post-show thank-you. | Repost artist/venue/radio Stories promptly. Capture permitted lobby/venue content and audience reaction with consent. | No performance footage, backstage access or family/private-property content without written permission. |

# 11. Paid media: hundreds, not thousands

Recommended working budget Use $450 as the planning model unless Forza is already covering the same platforms and audiences. Do not divide a small budget across every app. Use Meta plus one authorised TikTok Spark post. Do not buy followers, likes, generic 'awareness packages' or paid hashtag tools.

| Plan | Allocation | Use |
| --- | --- | --- |
| Lean — $300 | $250 Meta; $50 reserve | Use when Forza is running TikTok/artist ads. Keep two creatives and two audiences only. |
| Recommended — $450 | $300 Meta; $100 TikTok Spark; $50 reserve | Best balance for local Meta conversion plus one artist-led TikTok test. |
| Upper — $600 | $400 Meta; $150 TikTok Spark; $50 reserve | Only when the ticket page tracks sales and the winning creative is clear. |
| Tools | $0–$20 optional | Meta Business Suite, TikTok Studio and YouTube Studio are free. One month of Canva Pro is optional if it saves editing time. |

Spending timetable

| Dates | Share of budget | Action |
| --- | --- | --- |
| 20–29 July | 0–10% | Set-up; do not spend until the ticket link, tracking and approved creative are live. |
| 30 July–9 August | 20–25% | Test two clips: one joint and one individual; one broad local audience and one comedy-interest audience. |
| 10–20 August | 30–35% | Move spend to the best clip/audience combination; use partnership/Spark permissions where available. |
| 21–29 August | 45–50% | Use the best creative plus retargeting; preserve enough budget for the final 72 hours. |

Meta campaign set-up

[ ] Use Ads Manager, not a casual Boost button, for the main campaign.

[ ] Objective: Sales/Purchases when the ticketing provider can record them; otherwise Landing Page Views/Traffic.

[ ] Run no more than two ad sets at first: Broad local and Comedy/podcast interest.

[ ] All genders. Until age guidance is confirmed, start at age 25+; do not target minors.

[ ] Use two or three creatives only: joint video, Brendan clip and Mike clip. Static flyer is the fallback, not the lead.

[ ] If Forza supplies artist Partnership Ad permission, use the artist post rather than duplicating it from 1140-A.

[ ] Check the ticket page on mobile before spending.

Geography: Boston to the Mid-Cape

| Area | Locations |
| --- | --- |
| A. Cape / Upper–Mid Cape | Bourne, Sandwich, Falmouth, Mashpee, Barnstable/Hyannis, Yarmouth and Dennis; add a practical radius around the confirmed venue. |
| B. Plymouth / South Shore corridor | Plymouth, Kingston, Duxbury, Marshfield, Pembroke, Hanover, Norwell, Hingham, Weymouth, Braintree and Quincy. |
| C. Boston metro south | Boston plus southern neighbourhoods/cities such as Dorchester, South Boston, Jamaica Plain, Milton, Randolph and Canton; use only after Cape/South Shore coverage is protected. |
| Budget rule | Do not make three tiny ad sets if the total budget is $300. Combine A+B first; add C only when budget or Forza support permits. |

Audience settings

[ ] Broad local ad set: location + age only; allow the platform to find comedy buyers.

[ ] Interest ad set: stand-up comedy, comedy clubs, comedy podcasts and relevant comedy creators/podcasts where the platform offers them.

[ ] Possible interest names to test if available: Are You Garbage, Chris Distefano, Stavvy's World, Dan Soder, Comedy Cellar, Don't Tell Comedy, New York Comedy Club and GaS Digital.

[ ] Do not stack so many interests that the audience becomes tiny.

[ ] Retarget from 17 August: video viewers, Instagram/Facebook engagers, site visitors and checkout starters where tracking permits.

TikTok paid action

[ ] Use one Spark Ad from Mike or a joint post, not a generic 1140-A upload, when Forza supplies authorisation.

[ ] Target the same geographic corridor; all genders; age 21+/25+ depending approved age guidance.

[ ] Use comedy interests/behaviour and Smart Targeting without relaxing location or age controls.

[ ] If Forza is already running TikTok ads, do not duplicate. Give Forza the geography, ticket link and UTM naming instead.

Tracking links

Examples Instagram organic: [TBD URL]?utm_source=instagram&utm_medium=organic&utm_campaign=cape_aug29 Meta paid: [TBD URL]?utm_source=meta&utm_medium=paid&utm_campaign=cape_aug29&utm_content=joint_clip TikTok paid: [TBD URL]?utm_source=tiktok&utm_medium=paid&utm_campaign=cape_aug29&utm_content=mike_spark Radio/social partner: use one source code or UTM per partner.

# 12. Weekly workflow, engagement and decisions

Monday batch — 60 to 90 minutes

[ ] Select three approved clips and one Story/graphic theme.

[ ] Cut one clean 9:16 master per clip; export without platform watermark.

[ ] Write captions using the template bank; insert correct tags and links.

[ ] Schedule Instagram/Facebook in Meta Business Suite, TikTok in TikTok Studio and YouTube in YouTube Studio.

[ ] Prepare two Story frames for each feed post.

[ ] Send any artist Collab requests and final approval questions immediately.

[ ] Update the content tracker: date, platform, asset, rights, link, status and results.

Daily check — ten minutes

[ ] Reply to genuine comments and DMs the same day.

[ ] Like/reply to relevant artist, partner, radio and local-event posts.

[ ] Repost useful artist/podcast/press content to Stories with the ticket link.

[ ] Hide/report scams, fake ticket sellers, slurs and impersonation.

[ ] Escalate refunds, accessibility, age-policy and venue questions to the 1140-A owner.

[ ] Record important questions for the next FAQ Story.

Sunday review — 15 minutes

| Measure | Action |
| --- | --- |
| Views / reach | Record, but do not choose a winner on views alone. |
| Average watch / completion | Choose openings that hold attention. |
| Shares and saves | Strong signal for clips worth re-cutting, reposting or paying behind. |
| Profile visits | Check whether the content drives people to 1140-A. |
| Ticket-link clicks | Primary social signal when purchase data is unavailable. |
| Orders / tickets by source | Primary conversion measure where tracking works. |
| Comments / DMs | Turn repeated questions into FAQ content. |
| Partner reposts | Record artist, radio, venue and media amplification separately. |

Decision rules

[ ] A clip with roughly twice the account's median shares, saves or ticket clicks becomes the next paid/re-cut candidate.

[ ] High views but weak ticket clicks: strengthen the end-card, caption and link placement before spending more.

[ ] Strong clicks but weak sales: test the checkout on mobile and review audience/price information before increasing spend.

[ ] Three or more versions of the same question: publish an FAQ Story within 24 hours.

[ ] Artist or radio repost: reply, thank, share to Story and record the resulting ticket clicks.

[ ] Weak post: do not delete merely for low views. Leave it, learn, and replace the format next time unless it contains an error.

Saved replies

| Question | Reply |
| --- | --- |
| Tickets | Official tickets are available only at [TBD SHORT URL]. |
| Venue | The venue and town are [TO BE DETERMINED / INSERT APPROVED FACT]. |
| Age/content | The approved age/content guidance is [TO BE DETERMINED]. |
| Accessibility | Please contact [TBD] for accessibility arrangements. |
| Parking | Parking information: [TO BE DETERMINED]. |
| Scam warning | Please use only the official 1140-A ticket link. We do not sell tickets through comments or direct-message payment requests. |

# 13. Event-day social plan

| Time | Core post | Notes |
| --- | --- | --- |
| 8.00–9.00 a.m. | TONIGHT Reel/graphic on IG, FB and TikTok | Names, date, venue/town, time and official ticket link. |
| Noon | Story: practical information | Parking/access/doors/age guidance only when confirmed. |
| 3.00–4.00 p.m. | Final ticket Story | Use truthful availability; never invent scarcity. |
| Set-up | Venue/lobby/lighting Story | No private accommodation, family travel or backstage material. |
| Doors | Short welcome Story | Film patrons only with appropriate consent; avoid obstructing entry. |
| During show | No routine posting | No set footage or joke audio unless the written artist/venue permission explicitly allows it. |
| After show | Thank-you post/Story | Approved room/lobby photograph, tags and one line about the non-profit mission. |
| Next morning | Optional recap | Approved photographs, truthful attendance/sell-through and future-newsletter invitation. |

Do not post

[ ] Exact cottage/property location, family arrangements, arrival/departure details or private travel information.

[ ] Full or substantial portions of either stand-up set.

[ ] Unapproved backstage, dressing-room or green-room material.

[ ] Claims that the comedy is clean or family-friendly unless Forza approves that exact description.

[ ] Unconfirmed ticket price, venue, merchandise, sponsor, clam-bake or VIP information.

[ ] Artificial scarcity, false sell-out claims or ticket counts not verified by the ticketing system.

[ ] Downloaded clips or music without rights for the intended organic/paid use.

[ ] Other-platform watermarks, 15–30 hashtag blocks, irrelevant celebrity tags or purchased engagement.

Accessibility and presentation

[ ] Captions on every video.

[ ] Alt text on static images where the platform offers it.

[ ] High-contrast type; no small text over busy images.

[ ] Spell out venue and town; avoid unexplained abbreviations.

[ ] Do not flash text rapidly or place essential copy under interface buttons.

[ ] Use 'August 29' in public-facing graphics for the US audience, while this plan remains in British English.

Optional sponsor, merch and clam-bake module

| Item | Maximum social treatment before the event |
| --- | --- |
| Sponsor | One announcement/co-branded post, one Story thank-you, one event-day tag. Keep sponsor content below roughly 10% of the feed. |
| Merchandise | One post only after item, image, price, stock, sales point and payment method are final. |
| Clam-bake/VIP | One dedicated post only after capacity, price, inclusion/exclusion, timing and eligibility are final. Do not imply every ticket includes it. |
| Charity partners | Quiet Story/tag or post only with their consent; do not turn confidential ticket placement into public performance. |

# 14. Ready-to-copy content bank

Account bio

Cape-based non-profit presenting live stand-up comedy. Brendan Sagalow + Mike Cannon • August 29 • Cape Cod. Tickets: [TBD SHORT URL]

Launch caption

CAPE COD: Brendan Sagalow and Mike Cannon are together for one night on Saturday, August 29. [VENUE/TOWN – TBD]. Tickets: [TBD SHORT URL]. @brendansagalow @iammikecannon @fartcarnival #1140AComedy #CapeCodComedy #CapeCodEvents #StandUpComedy

Brendan clip

This is Brendan Sagalow. See him live on Cape Cod on August 29 with Mike Cannon. [VENUE/TOWN – TBD]. Tickets: [TBD SHORT URL]. @brendansagalow @iammikecannon #1140AComedy #CapeCodComedy #StandUpComedy

Mike clip

This is Mike Cannon. See him live on Cape Cod on August 29 with Brendan Sagalow. [VENUE/TOWN – TBD]. Tickets: [TBD SHORT URL]. @iammikecannon @brendansagalow #1140AComedy #CapeCodComedy #StandUpComedy

Joint/podcast clip

The chemistry is already built in. Brendan Sagalow + Mike Cannon — long-time collaborators and Fart Carnival co-hosts — together on Cape Cod, August 29. Tickets: [TBD SHORT URL]. @fartcarnival @brendansagalow @iammikecannon #1140AComedy #FartCarnival #CapeCodComedy

Local/non-profit post

A Cape-based non-profit. A proper live stand-up night. Two nationally touring New York comedians. Brendan Sagalow + Mike Cannon • Cape Cod • August 29. Tickets: [TBD SHORT URL].

Facebook-group post

Cape Cod comedy night on Saturday, August 29: Brendan Sagalow and Mike Cannon are appearing together in [TOWN/VENUE – TBD]. The event is presented by Cape-based non-profit 1140-A. Details and official tickets: [TBD URL]. Admins: please remove if event posts are not permitted.

One week

ONE WEEK: Brendan Sagalow + Mike Cannon on Cape Cod next Saturday, August 29. [VENUE/TOWN – TBD]. Tickets: [TBD SHORT URL].

Tomorrow

TOMORROW: Brendan Sagalow + Mike Cannon on Cape Cod. [VENUE/TOWN – TBD] • [TIME – TBD] • tickets: [TBD SHORT URL].

Tonight

TONIGHT: Brendan Sagalow + Mike Cannon on Cape Cod. [VENUE/TOWN – TBD]. Doors [TBD] • show [TBD] • official tickets: [TBD SHORT URL].

Supporter share text

I am helping spread the word about a new Cape-based non-profit comedy event: Brendan Sagalow and Mike Cannon, together on Cape Cod on August 29. Details and tickets: [TBD SHORT URL].

Forza launch request

We plan to publish the joint launch at [TIME] ET on July 21 from [ORIGIN ACCOUNT]. Please confirm the final caption, approved tags and whether Brendan and Mike can accept/share the Instagram Collab request within 30 minutes. We will use the same approved clean master natively on Facebook, TikTok and YouTube Shorts.

Spark/partnership request

Please provide Meta Partnership Ad permission/code and a TikTok Spark authorisation code for [POST URL]. Requested window: 60 days, event promotion only, budget not to exceed [TBD]. No account password is required.

# 15. Final checklists

Before the first post

[ ] All account handles, bios, profile images and links match.

[ ] Ticket page works on a phone and preserves tracking parameters.

[ ] Venue/town, time, price, age guidance and accessibility facts are approved or marked TBD.

[ ] Forza has approved billing, photos, clips, captions and rights.

[ ] Launch Collab origin, time and acceptance process are agreed.

[ ] Facebook Event is complete and not duplicated.

[ ] Comment/DM saved replies and scam warning are ready.

[ ] Content for the next seven days is scheduled.

Every post

[ ] Correct names, date, Cape Cod location and current ticket link.

[ ] Approved source and rights.

[ ] Face/hook in first two seconds for video.

[ ] Captions checked.

[ ] End-card and local location tag.

[ ] Correct @mentions; three to five relevant hashtags at most.

[ ] No unconfirmed price, venue, merch, sponsor or clam-bake details.

[ ] Scheduled result logged after 24–48 hours.

Final 72 hours

[ ] All platform bio links tested.

[ ] One final Forza/artist share confirmed.

[ ] Top paid creative and retargeting active; no new untested campaign structure.

[ ] Practical information graphic approved.

[ ] Official ticket-source/scam warning posted.

[ ] Event-day filming and photography permissions in writing.

[ ] Post-show thank-you graphic and folder ready.

The workable minimum Three good short videos per week; daily Stories in the final fortnight; one strong Collab launch; one Facebook Event; local-group placement; prompt replies; one clean paid Meta campaign; and one artist-authorised TikTok or Meta ad when available.

# 16. Sources and current platform mechanics

Platform features change. These official references were checked on 18 July 2026. The working plan should be re-checked inside each app before launch.

• Campaign data: Uploaded workbook: Sagalow_Cannon_Social_Stats_v2_Sponsor.xlsx, figures pulled 18 July 2026.

• [M1] Instagram Collab posts — official platform guidance

• [M2] Instagram native Reposts and location-tagged discovery — official platform guidance

• [M3] Meta Partnership Ads — official platform guidance

• [M4] Partnership Ad permissions/codes — official platform guidance

• [M5] Instagram shared access — official platform guidance

• [M6] Instagram reach: relevant keywords in content, captions, bio and hashtags — official platform guidance

• [M7] Instagram Trial Reels — official platform guidance

• [T1] TikTok Repost — official platform guidance

• [T2] TikTok Studio scheduling and analytics — official platform guidance

• [T3] TikTok Spark Ads — official platform guidance

• [T4] Spark code creation — official platform guidance

• [T5] TikTok targeting and Smart Targeting — official platform guidance

• [Y1] YouTube scheduled publishing — official platform guidance

• [Y2] YouTube @mentions — official platform guidance

• [Y3] YouTube Shorts external links — official platform guidance

• [Y4] YouTube Shorts remixing — official platform guidance

• [X1] X Repost and Quote Post — official platform guidance

Local account references

• Cape Cod Times — official Instagram account

• Visit Cape Cod — official Instagram account

• Cape Cod Chamber — official Instagram account

• Cape Cod Life — official Instagram account

• Cape Cod Community College — official Instagram account

Version note This plan assumes Saturday, 29 August 2026. Replace every TBD field only with approved final information. Re-check platform buttons and permissions in-app before executing any Collab, Repost, Partnership Ad or Spark Ad.